## GAR Booklet process
Sub process | # | Activity | How | Why | Who | When | Duration | Output stored at | Job instruction sheet | Remarks
1. GAR Booklet preparation
| 1.1 | Send the booklet timeline e-mail | Update the e-mail text for the current quarter and send it: Dear all, please be informed of the QX YYYY GAR Booklet timeline: Open: WD7 – [day, date], 10:00 Close: WD10 – [day, date], 13:00 Pre-review: WD10 – [day, date], 14:00 Review: WD11 – [day, date], 09:00 RCF meeting: WD12 – [day, date], 09:00 Please update the comments on your slides in Tangelo and set the slide status once it is completed. | To inform the contributors when their information must be ready. | GAR Intern | WD1 | 5 min | Outlook | n/a | Send to all slide owners as per the responsibility matrix slide in Tangelo. Check the WD numbers against the closing calendar (e.g. Q3 2026: Fri 9 Oct = WD7, so Wed 14 Oct = WD10).
| 1.2 | Create the booklet in Tangelo for the new quarter | In Tangelo, copy last quarter's booklet, keep the GAR booklet data source, rename the copy to the new quarter (description field) and save. For details and screenshots, see the job instruction sheet, section “How to create the presentation for the new quarter”. | To create the booklet for the new quarter from last quarter's version. | GAR Intern/Professional | Around the 18th of the last month of the quarter | 20 min | Tangelo – GAR Booklet folder | JIS.18.3.7.RP.04.02 – Create GAR booklet in Tangelo | Only owners of the file can lock and unlock it.
| 1.3 | Roll forward the booklet Excel and refresh the EFR queries | 1) Copy the Excel booklet on the Drive and rename it to the new quarter. 2) Follow the instructions in the Excel (incl. the manual input step: update the previous-quarter figures and the headers, e.g. Q2 – Q3) and tick each completed step in the column on the right. 3) Refresh the EFR queries. | To load the current quarter's financial data. | GAR Intern/Professional | Same day as 1.2, and again on WD7 and WD8 | 30 min | Z:\ConsolidationReporting\GAR\Reporting\GAR Booklet | Instructions tab in the Excel booklet
| 1.4 | Check the booklet Excel | 1) Go to each sheet and check that all “Check” cells are zero. If not, look at the formula and find the cause. Differences below 0.500 are rounding differences. 2) In every table, expand the collapsed rows (+ sign). If the hidden rows contain values, keep them visible. | To make sure the figures are complete and correct before they go into Tangelo. | GAR Intern/Professional | Same day as 1.3 | 20 min | Z:\ConsolidationReporting\GAR\Reporting\GAR Booklet | n/a
| 1.5 | Upload and synchronise the Excel in Tangelo | In Tangelo, go to Data source → GAR Booklet, select the new Excel file and click play until the bar is green and shows “ready”. Then open the booklet and click both synchronise buttons until the line turns green. For details and screenshots, see the job instruction sheet, section “Steps to upload and synchronize the excel file” (steps 1–4). | To load the Excel figures into the Tangelo booklet. | GAR Intern/Professional | Same day as 1.3 | 5 min | Tangelo – GAR Booklet folder | JIS.18.3.7.RP.04.02 – Create GAR booklet in Tangelo | If the status bar does not turn green, contact Faizal.
| 1.6 | Check the booklet in Tangelo | 1) Perform the same checks as in step 1.4, now in Tangelo. 2) Update the front cover header to the current quarter and check all headers. For details, see the job instruction sheet, section “Steps to upload and synchronize the excel file” (step 5). | To make sure the synchronised booklet is complete and correct. | GAR Intern/Professional | Same day as 1.5 | 15 min | Tangelo – GAR Booklet folder | JIS.18.3.7.RP.04.02 – Create GAR booklet in Tangelo
| 1.7 | Inform the GAR team | Send an e-mail to the whole GAR team that the booklet for the new quarter is updated and open for input. | So slide owners know they can start updating their slides. | GAR Intern/Professional | Right after step 1.6 (WD7) | 5 min | Outlook | n/a
2. Pre-review
| 2.1 | Check the responsibility matrix | Go to the responsibility matrix and contact everyone whose slide does not have the status “done”. | To keep to the timeline and make sure all data is delivered on time for the GAR manager review. | GAR Intern/Professional | Before 10:00 on pre-review day | 10 min | Tangelo – GAR Booklet folder | n/a
| 2.2 | Check the index | Check that the page numbers in the index match the page numbers on each slide. | If slides were added or removed, the index must be realigned. | GAR Intern/Professional | Pre-review day | 10 min | Tangelo – GAR Booklet folder | n/a
3. Finalise and send to the auditor
| 3.1 | Generate the PDF | Check the formatting (no tables split over two pages, nothing hidden or cut, headers on the current quarter), then generate the PDF in Tangelo with the Acrobat button. Save the PDF in the quarter folder using the naming convention of previous quarters. For details, see the job instruction sheet, section “Steps to generate the pdf”. | To produce the final version of the booklet. | GAR Intern/Professional | After the RCF meeting | 15 min | Z:\ConsolidationReporting\GAR\Reporting\GAR Booklet\YYYY\QX YYYY | JIS.18.3.7.RP.04.02 – Create GAR booklet in Tangelo
| 3.2 | Send the booklet to PwC | 1) Confirm with the GAR manager that the booklet can be sent. 2) Upload the PDF in PwC Connect. Do not send it by e-mail. | To provide the auditor with the final booklet. | GAR Intern/Professional | Day after the RCF meeting | 10 min | PwC Connect | n/a | Always check with the GAR manager first.